## Product Backlog - Meeting 1
Product Backlog | Bus Value | Effort | ROI
As a payment provider I want an accept Payment API available so that I can provide my services to online stores |  |  | 3.35
As a payment provider I want an Payment API available so that I can troubleshoot payment issues |  |  | 3.7
As a payment provider I want an Payment API available so that I can see all payments on a date |  |  | 3.92
As a payment provider I want Payment info in a database so that I can see all my data for reports |  |  | 5.1
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly |  |  | 4.7
As a hotel customer I want a webpage details page so that I can view my payment status |  |  | 3.3
As a hotel owner I want a payment details portal so that I can assist my customers |  |  | 6.53
As a hotel customer I want a user portal so that I can cancel my booking |  |  | 2.88
As a hotel customer I want a user portal so that I can edit my booking |  |  | 1.8

## Sprint Backlog 1
Product Backlog | Avg Bus V | Avg Effort | ROI
As a hotel customer I want a webpage page so that I can make online payment
As a hotel owner I want an online Payment option on my website so that I can process online payments
As a hotel customer I want a webpage page so that I can make online payment
Tasks | Effort
Define and Build Database schema | 8
Define (processPayment) API call | 8
Build API call - integrate with service | 3
Test API call - manual test for postman | 2
Integrate API with existing site | 2
Create form for entering Process Payment params | 3
Validation prior to sumbission | 2
Section for transaction results | 3
Integrate Testing | 3
Exit Criteria - Done
Sucessful payment
field vaidations
insufficient funds
Assume we have a website, assume guest reservation
Tasks
As a hotel owner I want an online Payment option on my website so that I can process online payments

## Product Backlog - Meeting 2
Product Backlog | Business Value | Effort | ROI
As a customer I want to get alerts on bookings and new deals so that I can know about deals | 8 | 2 | 4 | Bhavya
As a payment provider I want an Payment API available so that I can troubleshoot payment issues | 7.5 | 2 | 3.75 | Santhamohan
As a hotel owner I want a payment details portal so that I can assist my customers | 8 | 3.5 | 2.2857 | Bhagya
As a hotel customer I want a user portal so that I can cancel my booking | 9 | 4 | 2.25 | Vivek
As a hotel customer I want a user portal so that I can edit my booking | 9 | 4 | 2.25 | Ravneet
As a payment provider I want Payment info in a database so that I can see all my data for reports | 6.5 | 3 | 2.1667
As a customer I want to have member booking so that I can get special discounts off my booking | 6.5 | 3 | 2.1667
As a customer I want to have member booking so that I do not have to remember my contact info | 6 | 3 | 2
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction | 6 | 3 | 2
As a payment provider I want an accept Payment API available so that I can provide my services to online stores | 7.5 | 4 | 1.875
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly | 7.5 | 4 | 1.875
As a payment provider I want an Payment API available so that I can see all payments on a date | 6 | 3.5 | 1.7143
As a hotel customer I want a webpage details page so that I can view my payment status | 8 | 5 | 1.6
As a payment provider I want a payment API that can handle different tax rates | 6 | 4 | 1.5
As a owner I want to support loyality points to that customers can redeem for a deal | 7 | 5 | 1.4
As an owner I want to support A/B testing so that I can optimize ad placement for revenue | 5 | 4 | 1.25
As an owner I want to see what my customers are looking at, so that I can provide customer specific offers | 9 | 10 | 0.9
Note on D19: Dan Penny: Update Bus Value and Effort and ROI for all values

## Sprint Backlog 2
As a hotel owner I want a payment details portal so that I can assist my customers
Tasks | Efforts
Define and Build Database Schema | 2
formulate query to fetch payment details for customer | 1
Design Web page for payment detail | 5.5
Integrate query in payemnt detail webpage | 2
Test Connectivity and form validation | 1
Integrate with Website | 2
Integration Testing | 4
As a payment provider I want an Payment API available so that I can troubleshoot payment issues
Tasks | Efforts
Get the Protocol and Data Formats used in the Payment API from the Payment Provider | 5
Get the API Protocol from the list of Individual Payment Providers to Aplication Programmers (Sending requests over the Internet, and how to interpret the server's responses) | 6
Should build an alternate Payment API if fails(E-Wallet) | 3
Check if the Payment Provider has been disabled | 1
Build the Gateway Log to check if fails | 4
Test the Gateway with valid Card number information | 1
Check the following Connectivity issues
Firewall issues | 1
Proxy Configuration | 1
SSL Certificate issues | 1
Client Certificate issues | 1
Incorrect Request URLs | 1
Using incorrect protocol | 1
Invalid Postman behavior | 1
Check if the Timeouts are Very Short | 1
Incorrect or missing authentication details | 2
Payment method/currency not supported by this account number; accounts only support a single payment method/currency combination | 2
Delay Message from the API to the customer that, Transaction is in progress or was Declined | 4
Subtasks - As a user , I want to cancel my booking
Tasks | Efforts
Create a booking cancellation button on the webpage | 2
Formulate query to fetch cancellation details for booking. | 3
Create a module to refund the amount to the user. | 6
Create a module to set the current value of booking on the demand. | 8
Integrate with website | 2
Integration testing | 4
As a hotel customer I want a user portal so that I can edit my booking
Tasks | Efforts
Create a Edit Booking button on the webpage | 2
Formulate query to fetch the price difference and availablity. | 3
Create a module to update the modified price. | 6
Integrate with website | 2
Integration testing | 4
Integration testing
As a customer I want to get alerts on bookings and new deals so that I can know about deals
Tasks | Efforts
Administrative people will put details of the offers and it can be passed in the database table | 3
Define and Build Database Schema for offers & Customer Bookings | 3
By Integrating with SMS/E-Mail Gateway, customer will get alerts on Bookings and New Offers | 5
Integrate with website for the New offers (Banner) | 3
Integration testing | 4

## Team Members
Name | A# | Role
Person 1 | A00429943 | Maninder Kaur Baria
Person 2 | A00429112 | Santhamohan Manivannan
Person 3 | A00431152 | Bhagya Shree
Person 4 | A00425792 | Vivekanand Boopathy
Person 5 | A00426623 | Ravneet Singh Oberoi
Person 6 | A00428499 | Bhavya Ahuja

## Product Backlog - Meeting 3
Tasks | B-Value | Effor | ROI
As a hotel owner I want to see the resurant menu so that customers will know what food options there are | 6 | 2.75 | 2.1818
As a payment provider I want Payment info in a database so that I can see all my data for reports | 6.5 | 3 | 2.1667
As a customer I want to have member booking so that I can get special discounts off my booking | 6.5 | 3 | 2.1667
As a customer I want to have member booking so that I do not have to remember my contact info | 6 | 3 | 2
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction | 6 | 3 | 2
As a payment provider I want an accept Payment API available so that I can provide my services to online stores | 7.5 | 4 | 1.875
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly | 7.5 | 4 | 1.875
As a payment provider I want an Payment API available so that I can see all payments on a date | 6 | 3.5 | 1.7143
As a hotel customer I want a webpage details page so that I can view my payment status | 8 | 5 | 1.6
As a payment provider I want a payment API that can handle different tax rates | 6 | 4 | 1.5
As a customer I want to have an option to book a meeting hall so that I can book an event | 6 | 4 | 1.5
As a owner I want to support loyality points to that customers can redeem for a deal | 7 | 5 | 1.4
As a hotel owner I want to implement a live chat for employees so that I can assist my customers in real time | 6.5 | 5 | 1.3
As an owner I want to support A/B testing so that I can optimize ad placement for revenue | 5 | 4 | 1.25
As a customer I want to schedue an airport pickup so that I be picked up by the hotel airport shuttle | 3 | 2.75 | 1.0909
As a customer I want to get an email notification of payment so that I can have proof of payment | 2 | 2 | 1
As an owner I want to see what my customers are looking at, so that I can provide customer specific offers | 9 | 10 | 0.9
As a customer I want to see my pervious bookings so that I can see what I paid ( compare prices) | 3 | 4 | 0.75
As a hotel owner I want a special role so that I can have different access for different users ( admin/users) | 4 | 7 | 0.57143
As a customer I want to re-schedue an airport pickup so that I be picked up by the hotel airport shuttle | 1 | 1.75 | 0.57143

## Sprint Backlog 3
As a hotel owner I want to see the resurant menu so that customers will know what food options there are
Tasks | Efforts
Design & Buid the schema | 4
Create a new webpage for displaying the Food Menu | 2
Create a webpage for editing the menu for Managers | 2
Integrate Database with Website | 3
Integration Testing | 2
As a payment provider I want Payment info in a database so that I can see all my data for reports
Tasks | Efforts
Create a new webpage and link it with Tableau | 2
Create a module to fetch the Report from Database | 5
Integrate with Website | 2
Regression Testing | 4
As a customer I want to have member booking so that I do not have to remember my contact info
Tasks | Efforts
Design & Buid the schema | 4
Create a new webpage for User Profile | 2
Integrate Database with Website | 2
Regression Testing | 3
As a customer I want to have member booking so that I can get special discounts off my booking
Tasks | Efforts
Create a module to calculate the discount applicable as per the member privileage | 4
Integrate with current cost | 2
Regression Testing | 4