## Product Backlog - Meeting 1
Product Backlog | Bus Value | Effort | ROI
As a payment provider I want an accept Payment API available so that I can provide my services to online stores |  |  | 3.35
As a payment provider I want an Payment API available so that I can troubleshoot payment issues |  |  | 3.7
As a payment provider I want an Payment API available so that I can see all payments on a date |  |  | 3.92
As a payment provider I want Payment info in a database so that I can see all my data for reports |  |  | 5.1
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly |  |  | 4.7
As a hotel customer I want a webpage details page so that I can view my payment status |  |  | 3.3
As a hotel owner I want a payment details portal so that I can assist my customers |  |  | 6.53
As a hotel customer I want a user portal so that I can cancel my booking |  |  | 2.88
As a hotel customer I want a user portal so that I can edit my booking |  |  | 1.8

## Sprint Backlog 1
Product Backlog | Avg Bus V | Avg Effort | ROI
As a hotel customer I want a webpage page so that I can make online payment
As a hotel owner I want an online Payment option on my website so that I can process online payments
As a hotel customer I want a webpage page so that I can make online payment
Tasks | Effort
Define and Build Database schema | 8
Define (processPayment) API call | 8
Build API call - integrate with service | 3
Test API call - manual test for postman | 2
Integrate API with existing site | 2
Create form for entering Process Payment params | 3
Validation prior to sumbission | 2
Section for transaction results | 3
Integrate Testing | 3
Exit Criteria - Done
Sucessful payment
field vaidations
insufficient funds
Assume we have a website, assume guest reservation
Tasks
As a hotel owner I want an online Payment option on my website so that I can process online payments

## Product Backlog - Meeting 2
Product Backlog | Business Value | Effort | ROI
As a customer I want to get alerts on bookings and new deals so that I can know about deals | 8 | 2 | 4
As a payment provider I want an Payment API available so that I can troubleshoot payment issues | 7.5 | 2 | 3.75
As a hotel owner I want a payment details portal so that I can assist my customers | 8 | 3.5 | 2.2857
As a hotel customer I want a user portal so that I can cancel my booking | 9 | 4 | 2.25
As a hotel customer I want a user portal so that I can edit my booking | 9 | 4 | 2.25
As a payment provider I want Payment info in a database so that I can see all my data for reports | 6.5 | 3 | 2.1667
As a customer I want to have member booking so that I can get special discounts off my booking | 6.5 | 3 | 2.1667
As a customer I want to have member booking so that I do not have to remember my contact info | 6 | 3 | 2
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction | 6 | 3 | 2
As a payment provider I want an accept Payment API available so that I can provide my services to online stores | 7.5 | 4 | 1.875
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly | 7.5 | 4 | 1.875
As a payment provider I want an Payment API available so that I can see all payments on a date | 6 | 3.5 | 1.7143
As a hotel customer I want a webpage details page so that I can view my payment status | 8 | 5 | 1.6
As a payment provider I want a payment API that can handle different tax rates | 6 | 4 | 1.5
As a owner I want to support loyality points to that customers can redeem for a deal | 7 | 5 | 1.4
As an owner I want to support A/B testing so that I can optimize ad placement for revenue | 5 | 4 | 1.25
As an owner I want to see what my customers are looking at, so that I can provide customer specific offers | 9 | 10 | 0.9
Note on D19: Dan Penny: Update Bus Value and Effort and ROI for all values

## Sprint Backlog 2
As a hotel owner I want a payment details portal so that I can assist my customers
Tasks | Efforts
Define and Build Database Schema | 2
formulate query to fetch payment details for customer | 1
Design Web page for payment detail | 5.5
Integrate query in payemnt detail webpage | 2
Test Connectivity and form validation | 1
Integrate with Website | 2
Integration Testing | 4
As a payment provider I want an Payment API available so that I can troubleshoot payment issues
Tasks | Efforts
Get the Protocol and Data Formats used in the Payment API from the Payment Provider | 5
Get the API Protocol from the list of Individual Payment Providers to Aplication Programmers (Sending requests over the Internet, and how to interpret the server's responses) | 6
Should build an alternate Payment API if fails(E-Wallet) | 3
Check if the Payment Provider has been disabled | 1
Build the Gateway Log to check if fails | 4
Test the Gateway with valid Card number information | 1
Check the following Connectivity issues
Firewall issues | 1
Proxy Configuration | 1
SSL Certificate issues | 1
Client Certificate issues | 1
Incorrect Request URLs | 1
Using incorrect protocol | 1
Invalid Postman behavior | 1
Check if the Timeouts are Very Short | 1
Incorrect or missing authentication details | 2
Payment method/currency not supported by this account number; accounts only support a single payment method/currency combination | 2
Delay Message from the API to the customer that, Transaction is in progress or was Declined | 4
Subtasks - As a user , I want to cancel my booking
Tasks | Efforts
Create a booking cancellation button on the webpage | 2
Formulate query to fetch cancellation details for booking. | 3
Create a module to refund the amount to the user. | 6
Create a module to set the current value of booking on the demand. | 8
Integrate with website | 2
Integration testing | 4
As a customer I want to get alerts on bookings and new deals so that I can know about deals
Tasks | Efforts
Administrative people will put details of the offers and it can be passed in the database table | 3
Define and Build Database Schema for offers & Customer Bookings | 3
By Integrating with SMS/E-Mail Gateway, customer will get alerts on Bookings and New Offers | 5
Integrate with website for the New offers (Banner) | 3
Integration testing | 4

## Team Members
Name | A# | Role | Position
Person 1 | A00429943 | Maninder Kaur Baria | Product Owner
Person 2 | A00429112 | Santhamohan Manivannan | Scrum Master
Person 3 | A00431152 | Bhagya Shree | Team Lead
Person 4 | A00425792 | Vivekanand Boopathy | Developer
Person 5 | A00426623 | Ravneet Singh Oberoi | Developer
Person 6 | A00428499 | Bhavya Ahuja | Developer

## Product Backlog - Meeting 3
Tasks | B-Value | Effor | ROI
As a hotel owner I want to see the resurant menu so that customers will know what food options there are | 6 | 2.75 | 2.1818
As a payment provider I want Payment info in a database so that I can see all my data for reports | 6.5 | 3 | 2.1667
As a customer I want to have member booking so that I can get special discounts off my booking | 6.5 | 3 | 2.1667
As a hotel customer I want a user portal so that I can edit my booking | 9 | 4 | 2.25
As a customer I want to have member booking so that I do not have to remember my contact info | 6 | 3 | 2
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction | 6 | 3 | 2
As a payment provider I want an accept Payment API available so that I can provide my services to online stores | 7.5 | 4 | 1.875
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly | 7.5 | 4 | 1.875
As a payment provider I want an Payment API available so that I can see all payments on a date | 6 | 3.5 | 1.7143
As a hotel customer I want a webpage details page so that I can view my payment status | 8 | 5 | 1.6
As a payment provider I want a payment API that can handle different tax rates | 6 | 4 | 1.5
As a customer I want to have an option to book a meeting hall so that I can book an event | 6 | 4 | 1.5
As a owner I want to support loyality points to that customers can redeem for a deal | 7 | 5 | 1.4
As a hotel owner I want to implement a live chat for employees so that I can assist my customers in real time | 6.5 | 5 | 1.3
As an owner I want to support A/B testing so that I can optimize ad placement for revenue | 5 | 4 | 1.25
As a customer I want to schedue an airport pickup so that I be picked up by the hotel airport shuttle | 3 | 2.75 | 1.0909
As a customer I want to get an email notification of payment so that I can have proof of payment | 2 | 2 | 1
As an owner I want to see what my customers are looking at, so that I can provide customer specific offers | 9 | 10 | 0.9
As a customer I want to see my pervious bookings so that I can see what I paid ( compare prices) | 3 | 4 | 0.75
As a hotel owner I want a special role so that I can have different access for different users ( admin/users) | 4 | 7 | 0.57143
As a customer I want to re-schedue an airport pickup so that I be picked up by the hotel airport shuttle | 1 | 1.75 | 0.57143

## Sprint Backlog 3
As a hotel owner I want to see the resurant menu so that customers will know what food options there are
Tasks | Efforts
Build database schema for food options ( Schema for Regular Food /Drinks , Lounge and Bar Menu, Price details) | 3
Create a web page to display the food options | 2
- Scroller to display images of signature Cuisines , restaurants and Live Kitchen. | 1
- Reserve table module towards the right side of the page( option to select date, time and meal type | 1
Fetching the details from database to webpage | 1
Integrate the webpage with website | 2
Integration testing | 2
As a payment provider I want Payment info in a database so that I can see all my data for reports
Tasks | Efforts
Create a new menu for reports | 2
Build form for user defined search option - Between Dates - Location wise Data - Payment Methods | 6
Create a module to generate the JASPER Reports | 5
Integrate with Website | 2
Regression Testing | 4
As a customer I want to have member booking so that I can get special discounts off my booking
Tasks | Efforts
Create a database 'users' table schema (Name , age , Mobile, Email,Gender , startdate,duration,No of bookings done, discount slab) | 1
Create a webpage for member registration ( Signup Form ) integrate insert query to insert into users table | 1
Create a module to calculate the discount applicable as per the discount slab , integrate into the Reservation/Bookings page | 1
Integrate with query to fetch the cost ( which will return cost after discounts) while reservation. | 1
Regression Testing | 1
Integrate with website | 2
As a hotel customer I want a user portal so that I can edit my booking
Tasks | Efforts
Create a Edit Booking button on the webpage | 2
Formulate query to fetch the price difference and availablity. | 3
Create a module to update the modified price. | 6
Integrate with website | 2
Integration testing | 4
Integration testing | 2

## Product Backlog - Meeting 4
Tasks | B-Value | Effor | ROI
As a customer I want to be able to login using social media so that they have easy access | 7 | 2 | 3.5
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction | 6 | 3 | 2
As a hotel owner I want a search option based on dates so that customer can see room availibility | 6 | 3 | 2
As a customer I want to have member booking so that I do not have to remember my contact info | 6 | 3 | 2
As a payment provider I want an accept Payment API available so that I can provide my services to online stores | 7.5 | 4 | 1.875
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly | 7.5 | 4 | 1.875
As a payment provider I want an Payment API available so that I can see all payments on a date | 6 | 3.5 | 1.7143
As a hotel customer I want a webpage details page so that I can view my payment status | 8 | 5 | 1.6
As a customer I want events tab on the website so that I can get information on ongoing and scheduled evernts | 4 | 2.5 | 1.6
As a payment provider I want a payment API that can handle different tax rates | 6 | 4 | 1.5
As a customer I want to have an option to book a meeting hall so that I can book an event | 6 | 4 | 1.5
As a owner I want to support loyality points to that customers can redeem for a deal | 7 | 5 | 1.4
As a hotel owner I want to implement a live chat for employees so that I can assist my customers in real time | 6.5 | 5 | 1.3
As an owner I want to support A/B testing so that I can optimize ad placement for revenue | 5 | 4 | 1.25
As a customer I want to schedue an airport pickup so that I be picked up by the hotel airport shuttle | 3 | 2.75 | 1.0909
As a hotel owner I want my website to have B2B so that I connect to travel agents to offer them discouted rates | 2 | 1.85 | 1.0811
As a customer I want to get an email notification of payment so that I can have proof of payment | 2 | 2 | 1
As an owner I want to see what my customers are looking at, so that I can provide customer specific offers | 9 | 10 | 0.9
As a customer I want to see my pervious bookings so that I can see what I paid ( compare prices) | 3 | 4 | 0.75
As a hotel owner I want a user portal so that customers can book activities that hotels offer at the spa | 1 | 1.4 | 0.71429
As a hotel owner I want a special role so that I can have different access for different users ( admin/users) | 4 | 7 | 0.57143
As a customer I want to re-schedue an airport pickup so that I be picked up by the hotel airport shuttle | 1 | 1.75 | 0.57143
As a hotel owner I want a to provide the customer with a flexible refund process so that they can get instant refund in terms of points | 0 | 0 | 0
As a hotel owner I want to provide a complementary option for the first 5% of customers(per day) so that I can attract more customers | na | na | 0

## Sprint Backlog 4
As a customer I want to be able to login using social media so that they have easy access
Tasks | Efforts
Modify the Signup page with the icons of the Social networks | 1
Fetch API from Social Networking sites | 1
Create a Module to get the user profile from API by the following steps: | 3
-Client requests access and permissions Via sdk and Login
-User authenticates and approves permissions
-Acess token is returned to client
Integrate with existing 'users' data schema | 3
Integration Testing | 3
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction
Tasks | Efforts
Create a HTML form | 2
create a database schema | 2
Connect the form to the database so it can save every new entry in the form | 2
With the help of HTML and CSS, display the form to the website page | 1
Fetch the database entries to the feedback form. | 3
Integrate with website | 2
Regression Testing | 3
As a hotel owner I want a search option based on dates so that customer can see room availibility
Tasks | Efforts
As a hotel owner I want a search option based on dates so that customer can see room availibility
Tasks | Efforts
Make a schema for all the type of rooms and the no of rooms in each type . | 2
Create a module for getting option through which one has the option to pay the difference amount in case one decides to change dates . | 4
Creat link should be provided for that | 4
Create a moduke for offers which might pop up on the dates when the hotel does not have much of booking | 5
Use if retrieved through database . | 4
Integrate with website | 3
Regression Testing | 2
As a customer I want to have member booking so that I do not have to remember my contact info
Tasks | Efforts
Design & Buid the schema (defining constraints and relations in between table) | 4
Create a new webpage for User Profile (Easy to understand design using HTML5 & CSS3 ) | 2
Integrate Database with Website (Data passed from database to webpage through post sessions) | 2
Regression Testing | 3

## Retrospective
A# | Team Member | Position | What worked within the project | What did not work within the project
A00429943 | Maninder Kaur Baria | Product Owner | Most of the Subtasks were prioritized based on the Business Value | Due to Redundant tasks, important tasks are left behind.
A00429112 | Santhamohan Manivannan | Scrum Master | Able to divide the subtasks and convince the team about the feasibility and optimum efforts | Need little experience to give exact Business Values and efforts in Subtasks.
A00431152 | Bhagya Shree | Team Lead | Process Understanding and Team Collaboration | Redundant Tasks in Stories Understanding the Business Values and Efforts
A00425792 | Vivekanand Boopathy | Developer | We were able to bring a consensus on the steps involved and the efforts | We would like to implement the architectural best practices while enlisting the steps next time.
A00426623 | Ravneet Singh Oberoi | Developer | There was a healthy discussion of the various issues and ideas and finally a resolution was made | Use some of the latest tools to solve the problems
A00428499 | Bhavya Ahuja | Developer | Team work , discusssion , learnt how sprint works , learnt about the roles and responsibilities of every indivisual.